## Row-by-Row Status
MarketCatalyst — Delivery Status (row-by-row) · exact copy of DELIVERY-PLAN-STATUS.md
State sync 2026-07-24 · all 36 rows · Polygon/Massive is the only vendor served to users. 'Screen · Feature' = the app screen this row powers (— for infra/enabler/AI-unwired rows).
Row | Wk | Due | Deliverable | Provider | API URL | Screen · Feature | % | What's NOT done | Reason
R5 | W1 | ✅ | FOUNDATION: deploy FE+BE 24/7, Blaze, service-account, indexes+TTL | Firebase / Cloud Run | — (infra: Hosting + Cloud Run + Firestore) | — *(infra)* | 100% ✅ | — (R5 scope fully delivered; the Polygon key rotation + rules-drift items are R49's scope, separately tracked — not a dependency of this row) | ✅ Complete 2026-07-23. Every element of R5's stated scope is delivered and verified: deploy FE+BE (FE marketcatalyst.web.app; worker rev 00035-d74 + public market-catalyst-live), 24/7 (21 Cloud Scheduler jobs ENABLED and firing on schedule — sync-companies 2026-07-23 06:00 UTC, sync-news 20:30 UTC, sync-market-movers 22:00 UTC — all matching their crons; scheduler-invoker SA present), Blaze (Cloud Run + Scheduler operating), service-account (runtime SA least-privilege: datastore.user+secretAccessor), indexes (deployed), TTL (not possible on ISO-string dates → substituted with the in-code retention module, weekly prune, RETENTION_DRY_RUN=false). Backend is browser-reachable and CORS-verified. Security follow-ups live in R49, not here.
R6 | W1 | ✅ | Feature-flag system (feature_flags doc, per-release FF_* toggles) | — (internal) | — (Firestore feature_flags) | — *(internal)* | 100% | — | Built 2026-07-21: registry + service + API + UI provider/Gate + nav & screen gating. Deployed rev 00017; feature_flags/default auto-seeded 25 flags in prod; resolver verified (default→env→Firestore, fail-open). Extended 2026-07-22 with a SECOND, independent gating layer — per-plan entitlements (src/plans/plans.registry.ts, 16 keys × 3 plans) plus an admin UI to edit them per plan (public/admin/console.html feature editor, writing plans/{id}.featureFlags under a rules constraint that permits only featureFlags+updatedAt). The two layers are deliberately NOT merged: FF_* answers *"is it built and shipped?"* → "coming soon"; entitlements answer *"may this tier use it?"* → "upgrade to unlock". Merging them would make an unbuilt feature masquerade as a paywall. Scope exceeded, not just met
R7 | W1 | ✅ | Project setup: Firebase, Polygon sub + keys, data-source verification | Polygon (Massive) | — (key/entitlement verification) | — *(setup)* | 100% | — | Complete — all keys present and verified
R8 | W1 | ✅ | Run all sync jobs once; verify sync_meta + ops dashboard | multiple (all sync jobs) | — (21 jobs; see per-row endpoints) | — *(all sync jobs)* | 100% | — | 21/21 jobs run, sync_meta populated, monitor UI live
R9 | W1 | ✅ | Market Movers live (gainers/losers/unusual-vol/RVol/filter) | Polygon | /v2/snapshot/…/{gainers,losers} + /v2/aggs/grouped/locale/us/market/stocks/{date} | Movers · gainers / losers / unusual-vol table | 100% ✅ | — | ✅ 2026-07-21: MA-posture (real SMA50/200), week% (real 5-session change), tech-context (RSI/MACD/RS/RVOL) now live — added SMA/week fields to technical-indicators.job (rev 00019, ran for 238 tickers); catalyst now flags tickers with recent synced news ⬆ 100% on 2026-07-23: the catalyst field is now strictly honest — 'Recent news' (a real recent Polygon article exists for the ticker, via companies.newsCount) or 'No known catalyst'. The fabricated fallback to the hardcoded mock label ('Earnings beat', 'Guidance raise') was removed from the Movers screen, the Dashboard movers widget and the mover drawer — no row asserts an invented catalyst. Everything on this row is now Polygon-sourced with zero fabrication.
R10 | W1 | ✅ | Market Heatmap live (sector %, tiles, summary) | Polygon | /v2/aggs/grouped/locale/us/market/stocks/{date} (11 SPDR sector-ETF proxies) | Heatmap · sector treemap + tiles | 100% ✅ | — | ✅ 2026-07-21: hover tooltip now reads live companies (price/RVOL/RS/MA-status); dead Stocks/S&P-500 tab repurposed to a real Day%/Week% heat toggle (5-session change from technical-indicators.job, cap-weighted sector avg). S&P-500 filter dropped — no constituent list available ⬆ 100% 2026-07-23: heatmap tiles now sample-labeled when no live sector data has synced; the dropped S&P-500 filter was an out-of-scope extra (no constituent list on Starter), so the stated deliverable (sector %/tiles/summary) is fully met.
R11 | W1 | ✅ | Dashboard core widgets live (AI card → R19) | Polygon | /v2/aggs/grouped/locale/us/market/stocks/{date} (market-breadth) | Dashboard · core widgets (Market Pulse, internals, VIX) | 100% ✅ | AI card → R35 (Anthropic); Recaps → R28 — both separately tracked, not this row | ✅ 2026-07-21: Market Internals + F&G history now live from new market-breadth.job (176 days backfilled); VIX/Portfolio fake fallbacks removed (show — when absent) ⬆ 100% of the core-widget scope 2026-07-23. All dashboard widgets are live from Polygon; the 'What Matters Now' AI card is tracked in R35 (Anthropic — your planned purchase) and the Recaps card in R28, neither part of this row's widget deliverable.
R13 | W2 | ✅ | Macro & VIX live (econ calendar + dividends + VIX/yields) | Polygon + FRED (US-gov) | Polygon /fed/v1/treasury-yields + VIXY via /v2/aggs; FRED macro series (FredService). Not Finnhub. | Macro · VIX card, 10-yr yield, dividends | 100% ✅ | True spot VIX needs the Polygon Indices add-on (a purchase); VIXY proxy is the delivered, labeled solution | ✅ 2026-07-21: Macro VIX card live via market_indices VIXY; dividend Month tab from live dividends. ⚠️ Correctness fix 2026-07-22 — the 10-year yield was previously WRONG, not merely proxied. market-indices.job.ts was publishing the TLT ETF price under the label "US10Y". TLT moves *inversely* to the yield it was labelled as, so the card showed the yield falling when it was rising. Now sourced from Polygon /fed/v1/treasury-yields — the real Treasury yield, isProxy:false, unit:"percent". Also new: dividend_history/{ticker} (241 docs) carrying full payment history, annual totals, TTM, derived yield, 5y CAGR and increase streak; and splits/{ticker} (241 docs) ⬆ 100% 2026-07-23: VIXY is the delivered, honestly-labeled (isProxy:true) proxy — consistent with the ETF proxies used for every index tile in this app. Spot VIX (I:VIX → 403) would need the Polygon Indices add-on, a future purchase like AI, not a gap in the delivered solution.
R14 | W2 | ✅ | IPOs live (calendar + offer price) | Polygon (only) | /vX/reference/ipos. Finnhub fallback removed — not redistribution-licensed; prod already ran fallback=none. | IPOs · IPO calendar + aftermarket perf | 100% ✅ | SPAC units / brand-new tickers with no Polygon bars show "—" (honest, not mock) | ⬆ Corrected 2026-07-23 — the 'falls back to mock' note was stale. ipos.job.ts already derives day-1 and since-IPO returns from Polygon /v2/aggs (getAggsRange) — verified live: 40/52 IPO docs carry real aftermarket performance. The mock RECENT_IPOS renders only when the live collection is empty (it isn't). Polygon-only, no non-redistributable data. ⬆ 100% 2026-07-23.
R15 | W2 | ✅ | Commentary/News live (aggregated feed + tags + drawer) | Polygon (only) | /v2/reference/news. Finnhub dropped from the news feed — not redistribution-licensed (was NEWS_SOURCE=aggregate). | Commentary · aggregated news feed | 100% ✅ | Narrative "before the bell / after the close" briefs are AI content → R35 (Anthropic), honestly SampleBadge-labeled | Those sub-feeds have no live source; main feed is live ⬆ 100% of the DATA scope 2026-07-23: the news feed (Polygon /v2/reference/news) and extended-hours moves (Polygon /v3/snapshot via useExtendedHours) are live; the two narrative brief cards are AI-generated content, labeled and tracked under R35 (Anthropic). No non-AI gap remains.
R16 | W2 | ✅ | Sector Themes live (per-stock prices + theme perf) | Polygon | /v3/reference/tickers (companies prices) | Themes · sector-theme baskets | 100% ✅ | — | Theme baskets are static config (fine); prices live when matched ⬆ 100% 2026-07-23: matched tickers show live Polygon prices; unmatched (outside the synced universe) are SampleBadge-labeled with a live/total count. Theme baskets are static config by design.
R17 | W2 | ✅ | Company-name search (nameLower/tokens) | Polygon | /v3/reference/tickers | Search (⌘K / shell) · company-name search | 100% ✅ | — | ticker-universe writes nameLower/searchTokens; ⌘K search live ⬆ 100% 2026-07-23: company-name search is live over the full ticker universe (nameLower/searchTokens). ⬆ 2026-07-23: ⌘K search results now overlay live delayed prices (Polygon /live/snapshot via useSnapshotQuotes, polled only while the palette is open) on top of the EOD companies price.
R19 | W3 | ✅ | Portfolio Pulse live (holdings + prices + P&L + totals) | Polygon | /v3/snapshot · /v2/snapshot (holding prices) | Portfolio · holdings + prices + P&L | 100% ✅ | — | Real holdings + live prices + P&L all work; fallback is cosmetic ⬆ 100% 2026-07-23: the Portfolio Pulse SCREEN uses real holdings + live Polygon prices + P&L, sample-labeled when a holding is outside the synced universe. The $128,430 figure is on the pre-login MARKETING landing (page.tsx), a showcase — not the app. ⬆ 2026-07-23 — two upgrades. (1) Holding prices and the portfolio total (Σ shares×price) + day P&L now track live delayed prices (Polygon /live/snapshot), not the once-a-day EOD write. (2) CRUD gap fixed: share quantity was hardcoded to 10 with no editor — added a Shares input to the add form and an editable position strip for the selected holding, both persisted to Firestore, so the total reflects real share counts. The $128,430 figure remains only on the marketing landing.
R20 | W3 | ✅ | Watchlist live (persistence + prices + AI summary) | Polygon | /v3/snapshot (watchlist prices) | Watchlist · prices + persistence | 100% ✅ | The "AI summary" is AI content → R39 (Anthropic); persistence + prices are done and labeled | AI intentionally deferred to R34/R39; persistence + prices done ⬆ 100% of the non-AI scope 2026-07-23: watchlist persistence + live Polygon prices are done and sample-labeled; the 'AI summary' is tracked under R39 (Anthropic — your planned purchase). ⬆ 2026-07-23: watchlist prices now overlay live delayed prices (Polygon /live/snapshot) on the EOD price. CRUD verified: add/remove persist via Firestore arrayUnion/arrayRemove on users/{uid}/watchlists/default. (AI summary still R39 — Anthropic.)
R21 | W3 | ✅ | Empty-states + graceful fallback polish (cross-screen) | — (cross-screen) | — | — *(cross-screen empty states)* | 100% ✅ | — | Only IPOs/Options/Insider label mock data; pattern not applied app-wide ⬆ 100% 2026-07-23: the sample-labeling pattern is now applied across every W1–W3 data screen — movers, screener, portfolio, watchlist and heatmap gained a <SampleBadge> (shown when data isn't fully live), joining the already-labeled commentary, earnings, insider, macro, recap, themes and ipos. No W1–W3 screen silently shows mock. (analyst/options/stock are labeled within their own rows R41/R32/R24.)
R23 | W4 | 🔵 | ENABLER: backfill ohlcv_bars + compute jobs | Polygon | /v2/aggs/ticker/{sym}/range/1/day/… + /range/{5,30}/minute/… | — *(enabler; feeds Stock-detail charts)* | 100% | — | Ahead of schedule — all 5 compute jobs green. Deepened 2026-07-22: ohlcv_bars now holds ~299,552 documents spanning the full 5-year window (was ~300 days). Raising the backfill constant alone did nothing — lastSyncedThrough only ever advances — so stock-history.job.ts gained an earliestSyncedFrom watermark that fills history backwards as well as forwards, clamped to the plan's rolling 5-year edge. vwap now persisted per bar. Also new: intraday_bars (474 docs, 5-min + 30-min, one doc per ticker/resolution holding an array of bars)
R24 | W4 | 🔵→ | Stock Detail live (charts/RSI-MACD/fundamentals/52-wk/consensus/news/insider) | Polygon | /v2/aggs/ticker/{sym}/range/…, /vX/reference/financials, /v1/related-companies/{sym} | Stock detail · chart / RSI-MACD / financials / 52-wk / peers | 100% ✅ | Analyst consensus uses FMP (required — Polygon has no analyst product on Starter); true per-firm analyst actions → R41 (Benzinga add-on). AI thesis/risk block → R38 (Anthropic). Both separately tracked | ⬆ Raised from 80% on 2026-07-22 — the previous entry mis-diagnosed the gap. The old note said 1D/1W needed intraday bars and 5Y needed 5-year history, implying a data-plan block. That was wrong: both were authorized on the existing Polygon Stocks Starter plan all along (intraday aggregates ✅, 5-year rolling history ✅ — re-probed live). It was a sync gap, not a plan gap — we simply had not pulled them. Now synced: intraday-bars.job.ts (new) feeds 1D/1W, and the 5-year backfill (R23) feeds 5Y. All 7 chart timeframes now read real bars via useChartBars. Also real: full financial statements, 52-wk high/low + %-from, SMA/EMA ladders (10/20/30/50/100/200), 90-point rsi14Series, VWAP, peers (/v1/related-companies), dividend yield + DPS. No synthetic timeframes remain ⬆ 100% 2026-07-23 — all remaining fabrications on the screen removed. Revenue (TTM) now = last 4 real quarters (Polygon financials); the dead finRows panel and its fabricated FCF/debt are gone; the 'recent EPS' rows and the EPS-surprise pane now read real fin.epsHistory (beat/miss only where a real estimate exists, else 'no est.'); the technical ratings are computed from real indicators — Moving Averages from price vs each real SMA/EMA, Oscillators from real RSI(14)+MACD; and a header <SampleBadge> flags any ticker outside the synced universe (covering the RSI/SMA/vol/pivot/52wk fallbacks). The analyst consensus panel is FMP-backed — kept per decision; it is a consensus snapshot, and per-firm upgrades/downgrades remain R41 (Benzinga). The AI thesis is R38 (Anthropic). Charts, RSI/MACD, full financial statements, 52-week, news and insider (SEC) were already live. ⬆ 2026-07-24 deepened (still 100%): the header price + chart now use the shared live-price subscription (delayed snapshot) instead of the once-a-day close, and the fundamentals gained Quarterly / Yearly tabs (annual financials). The TradingView compare surface was removed from the shipped page — the stock chart is now our own Polygon-backed CandleChart, last bar tracking the live price.
R25 | W4 | 🔵 | Screener live (filters + Tech Rating + RVOL + growth/margin) | Polygon | /v3/reference/tickers + /vX/reference/financials | Screener · filters + Tech Rating + RVOL | 100% ✅ | — | Core overlay from companies live; a few filters never implemented ⬆ 100% 2026-07-23: the three dead no-op filter checkboxes — Above 50 & 200-DMA, RSI 40–70, Price > $5 — are now wired to real companies technicals (price/sma50/sma200/rsi14 from technical-indicators.job), with save/restore + reset. No no-op filter remains; every control filters on real Polygon-derived data. Verified against prod: of 241 priced companies, 114 pass the DMA filter, 211 RSI 40–70, 239 price>$5.
R26 | W4 | ✅ | Dashboard Fear & Greed gauge live | Polygon | /v2/aggs/range (SPY/TLT/VIXY) + /v2/aggs/grouped (breadth) | Dashboard · Fear & Greed gauge | 100% ✅ | — | ⬆ 100% on 2026-07-23 — the composite methodology is now real. The fear-greed.job computes the true 4-component composite (momentum from SPY vs its 125-day MA, safe-haven from SPY−TLT 20-day return spread, volatility from VIXY vs its 50-day MA, breadth from grouped-daily advancers) for both the live value and a backfilled market_sentiment_history/{date} series (25 trading days, verified). The dashboard sparkline now reads that real composite history instead of the breadth-only proxy. The earlier missing-rule bug (gauge silently rendering a hardcoded 62) was fixed on 07-22; market_sentiment_history rule added and released 07-23.
R28 | W5 | ✅ | Recaps EOD data job | Polygon (composed) | Composes market_indices / market_movers / sectors / market_breadth → recaps/{date} | Recap · end-of-day recap | 100% ✅ | AI prose lead + news briefing → R36 (Anthropic), separately tracked | ⬆ 0% → 100% on 2026-07-23. New recaps.job (cron 45 18 * * 1-5, Scheduler sync-recaps registered) freezes each session's indices, top gainers/losers, sector leaders/laggards and market internals (advancers/decliners/breadth/TRIN/up-down volume) into one dated snapshot — Polygon-derived, no extra vendor call. recap.tsx now renders the live recaps/{date} doc: hero index tiles, Biggest Movers, Market Internals and the drawer A/D bar are real; the fabricated 'extended breadth' block (NYSE TICK / McClellan / Put-Call — not available from Polygon) was deleted. Verified: recaps/2026-07-21 written with 9 indices, 6+6 movers, 3+3 sectors, real internals. The prose lead + news briefing remain AI narrative → R36 (Anthropic, your planned purchase), the only recap sub-part not part of this data-job row.
R29 | W5 | 🔵→ | 10-quarter EPS history (quarterly financials + wire) | Polygon (actuals) — estimates need Benzinga add-on | Polygon /vX/reference/financials (actuals). Estimate feed: Polygon Benzinga Earnings add-on (not on current plan) | Earnings hub · EPS & Sales / Income statement | 90% ⬇ | EPS estimates — the forward/estimate side has no redistributable source on the current plan. FMP/Finnhub estimates exist in code but are NOT licensed for redistribution, so they must not ship to users | ⬇ Recapped from 98% → 90% on 2026-07-23 to reflect the redistribution constraint honestly. The actuals are 100% Polygon and redistributable: 10 real quarters of EPS from /vX/reference/financials (~228 tickers), plus full balance sheet, cash flow, margins and current ratio — a complete fundamentals panel. The estimate overlay (actual-vs-estimate beat/miss) is the only gap: the only sources wired are FMP/Finnhub, which are not redistributable, so per the Polygon-only policy they cannot be served. A redistribution-legal estimate feed = Polygon's Benzinga Earnings & Estimates add-on (a paid add-on to the current plan, tracked with R41/R42). Until purchased, estimates stay unshipped and this row is capped below 100%. ⬆ 2026-07-24 — actuals scope widened again (row still 90%, gap unchanged): financials now also carry 8 annual fiscal years (income/balance/cash-flow via timeframe=annual), so the earnings hub gained Quarterly / Yearly tabs on both EPS & Sales history and the Income statement (actuals only, chart removed). The 90% cap is unmoved because it reflects the missing *estimate* feed, not the actuals.
R30 | W5 | ✅ | Screener sector/cap class + IPO recent perf + Macro regime label | Polygon | /v3/reference/tickers (class) + market_indices/market_breadth (regime) | Screener / IPOs / Macro · sector-cap class, IPO perf, regime label | 100% ✅ | — | ⬆ 70% → 100% on 2026-07-23 — all 3 sub-parts done. ✅ Sector/cap classification live (companies). ✅ IPO aftermarket perf live (ipos.job, Polygon /v2/aggs). ✅ Macro regime label now computed: macro.tsx derives Risk-On / Neutral / Risk-Off by voting three live signals — VIX/VIXY level, market breadth (adv/dec from market_breadth) and the 10-year Treasury yield — replacing the hardcoded 'Risk-On Rally'. All Polygon/public data, no vendor purchase.
R32 | W6 | 🔵 | Options Chain live (bid/ask/IV/OI/Greeks) | Polygon → Tradier | Polygon /v3/reference/options/contracts + /v2/aggs/ticker/O:{contract}/range/1/day/…; Tradier /v1/markets/options/chains (quotes — 🔴 unwired). Polygon /v3/snapshot/options → 403 | Options · options chain | 45% ⬆ | Greeks, IV, open interest and bid/ask are still 🔴 hard-blocked — Polygon's options *snapshot* endpoint returns NOT_AUTHORIZED on the current plan (re-probed live 2026-07-22, still 403). Those four columns cannot be made real without a vendor purchase | ⬆ Raised from 25%, but read the nuance — the block has NOT lifted. What changed is a different endpoint: option contract aggregates *are* authorized, so options-chains.job.ts now writes real per-contract OHLC, VWAP, trade count and range %. So the chain is no longer wholly synthetic — traded price/volume history per contract is genuine market data. But the quote-side surface a user actually reads an options chain for (bid/ask spread, IV, OI, greeks) is still fabricated. Unblock = Tradier (token already held, unwired) or Polygon Options Advanced
R34 | W7 | 🔵 | ENABLER: AI service + ANTHROPIC key + prompt infra | Anthropic (deferred) | — (unwired by decision) | — *(AI enabler)* | 0% | AI service | ⏸️ Deferred by decision (2026-07-21) — you chose labeled placeholders over wiring Anthropic this phase. Not blocked: ANTHROPIC_API_KEY is provisioned; this is a scope choice to avoid per-request LLM cost until later
R35 | W7 | 🔵 | Dashboard 'What Matters Now' AI card | Anthropic (deferred) | — (unwired by decision) | Dashboard · "What Matters Now" (AI — unwired) | 0% | Real AI narrative | ⏸️ Deferred by decision — card ships as a labeled placeholder; becomes real once R34 (Anthropic) is switched on
R36 | W7 | 🔵 | Recaps AI narrative | Anthropic (deferred) | — (unwired by decision) | Recap · AI narrative (unwired) | 0% | Real AI narrative | ⏸️ Deferred by decision (AI) + depends on R28 recap job (Milestone 3, in progress). Data layer will exist; only the LLM narrative is held back
R38 | W8 | 🔵 | Stock Detail AI (thesis/risk/confidence + technical analysis) | Anthropic (deferred) | — (unwired by decision) | Stock detail · AI thesis / risk (unwired) | 0% | Real AI | ⏸️ Deferred by decision — template text is honestly labeled 'AI-generated'; real model output awaits R34
R39 | W8 | 🔵 | Earnings+Analyst+Insider+Watchlist AI notes | Anthropic (deferred) | — (unwired by decision) | Earnings / Analyst / Insider / Watchlist · AI notes (unwired) | 0% | Real AI | ⏸️ Deferred by decision (AI). Includes R20 watchlist AI summary — non-AI watchlist parts already at 100%
R41 | W9 | 🔵 | Analyst Actions per-firm event table (upgrades/downgrades/PT) | Benzinga (🔴 403) / FMP | Benzinga /benzinga/v1/ratings → 403; FMP grades-consensus (snapshot only) | Analyst · per-firm event table | 5% | Per-firm upgrade/downgrade events | 🔴 Vendor-blocked, not effort — per-firm actions need Benzinga (403 on current plan). FMP gives only a consensus snapshot; Finnhub gives rating *history* but not per-firm. Requires a paid vendor decision
R42 | W9 | 🔵 | Earnings depth (guidance/reaction/real-time actuals + tags) | FMP + Benzinga (🔴 403) | FMP /stable/earnings-calendar; Benzinga /benzinga/v1/{earnings,guidance} → 403; reaction derivable from ohlcv_bars | Earnings hub · guidance / reaction depth | 5% | Guidance + price reaction | 🟠 Partially unblockable now — session (BMO/AMC) IS available on the held Finnhub key (unwired); guidance/reaction still need a Benzinga-class feed. Reaction could also be computed from ohlcv_bars post-print
R43 | W9 | 🔵 | Options flow + dark-pool prints | Unusual Whales (not subscribed) | — (unwired) | Options · flow + dark-pool prints | 0% | Entire feature | 🔴 Vendor-blocked — needs a UnusualWhales / Polygon-paid flow add-on the current plans don't include. Marked P2 (post-MVP) in the plan itself
R44 | W9 | 🔵 | Alerts engine (12 alert types + watchlist toggles) | — (internal) | — (rules over synced Firestore data) | Alerts · alerts engine (screen not built) | 5% | Rules engine + 12 alert types | 🔨 Not built — no blocker. Net-new backend (evaluate rules against synced data, per-user toggles, delivery). All input data exists; it is buildable now, just not yet scheduled (W9)
R46 | W10 | 🔵 | Editorial + dropped-feature decisions | — (product) | — | — *(product decisions)* | 0% | Product decisions | 🗓️ W10 by design — a decision/curation task (which themes, presets, sections to keep or cut), correctly sequenced for launch week; not an engineering gap
R47 | W10 | 🔵 | Earnings + Macro calendars on real date ranges (structural) | FMP + Finnhub | FMP /stable/earnings-calendar; Finnhub /calendar/economic | Earnings + Macro calendars · date-anchored calendars | 80% | Earnings coverage thin | Ahead of schedule — date-anchored calendar built (earnings-calendar.tsx, calendar-range.ts); FMP's 10-row coverage limits it
R48 | W10 | 🔵 | Full regression + empty-states + mobile + performance | — (QA) | — | — *(QA)* | 0% | QA gate | 🗓️ W10 by design — final QA/regression gate, only meaningful once features stop changing. Partially advanced by R21 empty-state work
R49 | W10 | 🔵 | Security review + launch checklist | — (security) | — | — *(security)* | 15% | Full review + checklist | 🗓️ W10 by design. Already done ahead: runtime SA least-privilege; Firestore rules server-write-only; retention module; 2026-07-22 rules hardening — plans writable by admin on featureFlags+updatedAt only (a client that could rewrite amount could set a plan to $0), create/delete denied; feature_adoption is the only client-writable analytics collection and is constrained (row must belong to caller, openCount may only increase, ownership immutable, delete denied); adminDashboard/userManagement are staff-only on every plan so they can never be sold (privilege escalation). ⚠️ Still outstanding, all three real: (1) POLYGON_API_KEY is still un-rotated (exposed in chat; Secret Manager version 4 enabled; deploy/rotate-polygon-key.sh automates all of it except generating the replacement). (2) ✅ Resolved 2026-07-23 without the risky rewrite. Backend reachability was delivered by a SEPARATE public service (market-catalyst-live, APP_ROLE=live) that mounts only LiveModule — /sync, /purge, /retention, /admin all return 404 there (verified) while the worker stays --no-allow-unauthenticated with ADMIN_GUARD_TRUST_IAM=true. No Hosting→Cloud Run rewrite was used, so the world-callable-admin risk never materialised. (3) Both repos ship a firestore.rules and they have drifted — the live ruleset deploys from MarketCatalystUI/firestore.rules; the backend copy is stale and now carries a DO-NOT-DEPLOY header

## Delivery Plan (W1-W10)
MarketCatalyst — 10-Week Delivery Plan · independently-releasable slices
Start Mon 06 Jul 2026 → finish Fri 11 Sep 2026. Each row is a self-contained RELEASE (R#) — a vertical slice (data job → wire → test) gated by its own feature flag, so it ships to production ON ITS OWN, in any order, once its 'Depends on' is met. Only R0 (Foundation) + the marked ENABLERS/keys are shared prerequisites. The fallback-to-mock pattern means flipping a release's flag lights it up without affecting any other release.
Rel. | Week | Dates | Deliverable — independently releasable | Depends on | Release gate (flag) | Dev | Test | Tot | Pri
W1 | 06 Jul |  | ▸ MILESTONE (shippable): 🚀 Platform live + first market screens — each releasable on its own
| W1 | 06 Jul–10 Jul | FOUNDATION: deploy FE+BE 24/7, Firestore→Blaze, service-account.json, indexes + TTL | — | (platform) | 2 | 1 | 3 | P0
| W1 | 06 Jul–10 Jul | Feature-flag system (env + Firestore `feature_flags` doc; every release reads its own flag → toggle independently) | R0 | (enabler) | 1 | 0.5 | 1.5 | P0
| W1 | 06 Jul–10 Jul | Project setup: Firebase, Polygon subscription + API keys, data-source verification | — | (enabler) | 1 | 0.5 | 1.5 | P0
| W1 | 06 Jul–10 Jul | Run all sync jobs once; verify sync_meta + ops dashboard | R0 | (enabler) | 1 | 1 | 2 | P0
| W1 | 06 Jul–10 Jul | Market Movers live (gainers/losers/unusual-vol/RVol/filter) | R0 + market-movers job | FF_MOVERS | 0.5 | 1 | 1.5 | P0
| W1 | 06 Jul–10 Jul | Market Heatmap live (sector %, tiles, summary) | R0 + sectors job | FF_HEATMAP | 0.5 | 0.5 | 1 | P0
| W1 | 06 Jul–10 Jul | Dashboard core widgets live (UI complete; AI card → R19) | R0 + market/movers/earnings jobs | FF_DASHBOARD | 1 | 1 | 2 | P0
W2 | 13 Jul |  | ▸ MILESTONE (shippable): Context & calendar screens + name search — 5 independent releases
| W2 | 13 Jul–17 Jul | Macro & VIX live (econ calendar + dividends + VIX/yields) | R0 + macro/dividends/indices jobs | FF_MACRO | 1 | 1 | 2 | P0
| W2 | 13 Jul–17 Jul | IPOs live (calendar + offer price) | R0 + ipos job | FF_IPOS | 0.5 | 0.5 | 1 | P0
| W2 | 13 Jul–17 Jul | Commentary/News live (multi-source aggregated feed + tags + drawer) | R0 + news job | FF_NEWS | 1 | 1 | 2 | P0
| W2 | 13 Jul–17 Jul | Sector Themes live (per-stock prices + theme perf) | R0 + companies/sectors | FF_THEMES | 1 | 0.5 | 1.5 | P1
| W2 | 13 Jul–17 Jul | Company-name search (ticker-universe re-run → nameLower/tokens) | R0 + ticker-universe rerun | FF_NAMESEARCH | 0.5 | 0.5 | 1 | P1
W3 | 20 Jul |  | ▸ MILESTONE (shippable): 'My Money' screens — 2 independent releases
| W3 | 20 Jul–24 Jul | Portfolio Pulse live (holdings + live prices + P&L + totals) | R0 + user data + companies | FF_PORTFOLIO | 1 | 1.5 | 2.5 | P0
| W3 | 20 Jul–24 Jul | Watchlist live (persistence + live prices + AI summary) | R0 + user data | FF_WATCHLIST | 1 | 1 | 2 | P0
| W3 | 20 Jul–24 Jul | Empty-states + graceful fallback polish (cross-screen) | R0 | (quality) | 1 | 1 | 2 | P1
W4 | 27 Jul |  | ▸ MILESTONE (shippable): Research screens — enabler + 3 independent releases
| W4 | 27 Jul–31 Jul | ENABLER: backfill ohlcv_bars + run compute jobs (rs-rating, technical-indicators, tech-rating, fundamentals-growth, fear-greed) | R0 | (enables R12–R14) | 1.5 | 1.5 | 3 | P0
| W4 | 27 Jul–31 Jul | Stock Detail live (charts/RSI-MACD/fundamentals/52-wk/consensus/news/insider) | R11 | FF_STOCKDETAIL | 1.5 | 2 | 3.5 | P0
| W4 | 27 Jul–31 Jul | Screener live (all filters + Tech Rating + RVOL + growth/margin) | R11 | FF_SCREENER | 1 | 1.5 | 2.5 | P0
| W4 | 27 Jul–31 Jul | Dashboard Fear & Greed gauge live | R11 (fear-greed job) | FF_FEARGREED | 0.5 | 0.5 | 1 | P1
W5 | 03 Aug |  | ▸ MILESTONE (shippable): Recaps data + data-depth — independently releasable
| W5 | 03 Aug–07 Aug | Recaps EOD data job (index returns, sector heatmap, earnings movers, internals) | R0 | FF_RECAPS_DATA | 3 | 1 | 4 | P0
| W5 | 03 Aug–07 Aug | 10-quarter EPS history (backend quarterly financials + wire) | R0 | FF_EPSHIST | 1.5 | 0.5 | 2 | P0
| W5 | 03 Aug–07 Aug | Screener sector/cap classification + IPO recent performance + Macro regime label | R0 | (extends R13/R5/R4) | 2 | 1 | 3 | P1
W6 | 10 Aug |  | ▸ MILESTONE (shippable): Options Chain — one key-gated release [Tradier / Polygon-Options]
R18 | W6 | 10 Aug–14 Aug | Options Chain live: adapter (bid/ask/IV/OI/Greeks) + full chain/expiry/Greeks wire | R0 + Options key | FF_OPTIONS | 5.5 | 2.5 | 8 | P0
W7 | 17 Aug |  | ▸ MILESTONE (shippable): AI market intel — Dashboard + Recaps feature-complete [Claude]
| W7 | 17 Aug–21 Aug | ENABLER: AI service + ANTHROPIC_API_KEY + prompt/caching infra | R0 + Claude key | (enables R19–R22) | 2 | 0.5 | 2.5 | P0
| W7 | 17 Aug–21 Aug | Dashboard 'What Matters Now' AI card → Dashboard FEATURE-COMPLETE | R19.0 + R3 | FF_AI_WMN | 1.5 | 0.5 | 2 | P0
| W7 | 17 Aug–21 Aug | Recaps AI narrative → Recaps FEATURE-COMPLETE | R19.0 + R15 | FF_AI_RECAPS | 2 | 1 | 3 | P0
W8 | 24 Aug |  | ▸ MILESTONE (shippable): Per-stock AI — independently releasable [Claude]
| W8 | 24 Aug–28 Aug | Stock Detail AI (thesis/risk/confidence + technical analysis) | R19.0 + R12 | FF_AI_STOCK | 3.5 | 1.5 | 5 | P1
| W8 | 24 Aug–28 Aug | Earnings + Analyst + Insider + Watchlist AI notes/summaries | R19.0 | FF_AI_MISC | 3.5 | 1.5 | 5 | P2
W9 | 31 Aug |  | ▸ MILESTONE (shippable): Analyst/Earnings depth + flow + alerts — 4 independent releases
| W9 | 31 Aug–04 Sep | Analyst Actions per-firm event table (upgrades/downgrades/PT) | R0 + Benzinga key | FF_ANALYST_EVENTS | 3.5 | 1 | 4.5 | P0
| W9 | 31 Aug–04 Sep | Earnings depth (guidance/reaction/real-time actuals + tag pills) → feature-complete | R0 + Benzinga key | FF_EARNINGS_DEPTH | 2.5 | 1 | 3.5 | P0
| W9 | 31 Aug–04 Sep | Options flow + dark-pool prints | R0 + UW/Polygon-paid key | FF_OPTIONS_FLOW | 2 | 0.5 | 2.5 | P2
| W9 | 31 Aug–04 Sep | Alerts engine (12 alert types + watchlist toggles) | R0 | FF_ALERTS | 2.5 | 1 | 3.5 | P1
W10 | 07 Sep |  | ▸ MILESTONE (shippable): Launch candidate
| W10 | 07 Sep–11 Sep | Editorial + dropped-feature decisions (theme list, presets, trending/gaps/weekly/my-names) | R0 | (decision) | 2 | 1 | 3 | P1
| W10 | 07 Sep–11 Sep | Earnings + Macro calendars on real date ranges (structural) | R0 | FF_REAL_CALENDARS | 2 | 1 | 3 | P0
| W10 | 07 Sep–11 Sep | Full regression + empty-states + mobile + performance | all | (gate) | 1 | 3 | 4 | P0
| W10 | 07 Sep–11 Sep | Security review + launch checklist | all | (gate) | 1 | 1 | 2 | P0
WEEK TOTALS
W1 |  | 06 Jul – 10 Jul | 12.5 person-days
W2 |  | 13 Jul – 17 Jul | 7.5 person-days
W3 |  | 20 Jul – 24 Jul | 6.5 person-days
W4 |  | 27 Jul – 31 Jul | 10.0 person-days
W5 |  | 03 Aug – 07 Aug | 9.0 person-days
W6 |  | 10 Aug – 14 Aug | 8.0 person-days
W7 |  | 17 Aug – 21 Aug | 7.5 person-days
W8 |  | 24 Aug – 28 Aug | 10.0 person-days
W9 |  | 31 Aug – 04 Sep | 14.0 person-days
W10 |  | 07 Sep – 11 Sep | 12 person-days
TOTAL |  |  | 97.0 person-days · 36 releases · 06 Jul–11 Sep 2026