## Vendor Overview
StockWise — API Vendor Overview & Coverage Summary
Vendor | Category | Free Tier | Paid Plan | Data Coverage % | Screens Covered | Est. Monthly Cost | Notes
Polygon.io | Quotes, OHLCV, Gainers/Losers, Indices, Block Trades | 5 req/min, 15-min delayed REST | $29/mo Starter | 78 | Ticker Strip, Dashboard, Movers, Heatmap, Stock Detail, Portfolio, Watchlist, Screener, Recaps, IPOs | $29/mo | Primary quote source. WebSocket + REST. Covers gainers/losers, sector aggregates, full OHLCV history. Scales to WS concurrent connections.
FMP (Financial Modeling Prep) | Earnings Calendar, Fundamentals, Sector Data, Analyst, Transcripts | 250 req/day, 5yr financials free | $99/mo Growth | 72 | Earnings Hub, Stock Detail, Screener, Dashboard, IPOs, Analyst (historical) | $99/mo | Best earnings calendar. Transcripts on paid plan. Sector/industry group data matches MarketSurge-style classification.
Benzinga | News, Analyst Ratings (real-time stream), Earnings Actuals | Basic headlines only — no API access | $149-299/mo | 65 | Analyst Actions, Commentary/News, Dashboard WMN, Earnings (real-time actuals) | $149-299/mo | Real-time analyst ratings WS + news. Best for category-tagged Why It Moves news. Required for analyst actions board.
Finnhub | Macro Calendar, Quotes (fallback), Company News (fallback) | 60 req/min, WS 50 symbols, economic calendar | Free / $11-99/mo | 40 | Macro & VIX, Dashboard (fallback), Stock Detail (news fallback) | Free | Free tier covers macro calendar completely. Use as quote fallback for MVP/dev. Economic calendar: best free option.
Tradier | Options Chains (full: strike, bid/ask, IV, OI, Greeks) | Free with brokerage account | $10-35/mo Pro | 30 | Options Chain screen | Free | Full call/put chain including Greeks. Free with brokerage account. Best cost option for options data.
Unusual Whales | Options Flow, Dark Pool Prints, Congressional Trades | Website only — no free API tier | $48/mo Advanced | 20 | Options Chain (unusual flow), Insider (dark pool) | $48/mo | Unusual options detection via flow scoring. Required for Phase 2 unusual activity board. Not MVP-critical.
SEC EDGAR | 13F Filings, Form 4 Insider Transactions, S-1 Filings | 100% free, 10 req/sec rate limit | Free | 25 | Insider & Institutional, IPOs (S-1 dates) | Free | All 13F-HR + Form 4 XML. Batch overnight to avoid rate limit. Zero cost.
Claude API (Anthropic) | AI Summaries, Market Copilot, Technical Analysis, WMN Card | N/A — token-based pricing | ~$3/1M tokens (Sonnet 4.6) | 45 | Dashboard WMN, Earnings AI, Stock Detail AI thesis, Analyst AI notes, Recaps, Copilot | ~$50-200/mo est. | Powers all AI features. claude-sonnet-4-6. Streaming via SSE. Earnings summaries, TA, WMN card, AI Copilot.

## Screen-Feature Matrix
StockWise — Screen x Feature x API Coverage Matrix
Monthly Cost -> |  |  | $29/mo | $99/mo | $149-299/mo | Free | Free | $48/mo | Free | ~$3/1M tokens
Screen | Feature / Data Point | Priority | Polygon.io | FMP | Benzinga | Finnhub | Tradier | Unusual Whales | SEC EDGAR | Claude API | Coverage % | Recommended Primary | Integration Notes | Integration Status | Live in UI? (verified 2026-07-12) | Verification Notes | Planned Week | Planned Dates
>> SHELL / TICKER STRIP
| Live index quotes (SPY, QQQ, DJI, IWM, VIX) | P0 | Primary | - | - | Fallback | - | - | - | - | 100% | Polygon | Polygon WS /stocks subscription. Finnhub free fallback. | Done (EOD, ETF proxy) | Live in UI | Dashboard Pulse strip reads market_indices (ETF proxies) | W1 | 13 Jul–17 Jul
| User auth session (sign-in, sign-out) | P0 | Live (Firebase) | - | - | - | - | - | - | - | 80% | Firebase (live) | Already live — Firebase Auth + Redux auth-slice. | Already Live (Firebase, pre-existing) | Already Live (unchanged, pre-existing Firebase) |  | W1 | 13 Jul–17 Jul
| User profile (name, image, tier) | P0 | Live (Firebase) | - | - | - | - | - | - | - | 80% | Firebase (live) | Already live — Firestore users/{uid} -> Redux profile-slice. | Already Live (Firebase, pre-existing) | Already Live (unchanged, pre-existing Firebase) |  | W1 | 13 Jul–17 Jul
| Theme preference (dark/light, font size) | P0 | Live (Firebase) | - | - | - | - | - | - | - | 80% | Firebase (live) | Already live — Firestore settings/{uid} + localStorage cache. | Already Live (Firebase, pre-existing) | Already Live (unchanged, pre-existing Firebase) |  | W1 | 13 Jul–17 Jul
>> DASHBOARD
| Market Pulse strip — 6 index prices & change % | P0 | Primary | - | - | Fallback | - | - | - | - | 100% | Polygon | Polygon /v2/snapshot/locale/us/markets/ticker. Finnhub fallback. | Done (EOD, ETF proxy) | Live in UI | dashboard.tsx reads market_indices | W1 | 13 Jul–17 Jul
| What Matters Now AI card (plain-English market summary) | P0 | Primary | - | Fallback | - | - | - | - | Primary | 100% | Polygon + Claude API | Claude API generates; Benzinga provides raw news context; Polygon provides prices. | Not yet built (in scope, no job written) | Not wired yet (screen not migrated) | Explicit "not wired" placeholder in dashboard.tsx - needs Claude (ANTHROPIC_API_KEY) | W6 | 17 Aug–21 Aug
| VIX level + day change | P0 | Primary | - | - | Fallback | - | - | - | - | 100% | Polygon | Polygon /v2/snapshot for $VIX ticker. Finnhub fallback. | Done (EOD, ETF proxy) | Live in UI | Dashboard VIX widget reads market_indices (VIXY ETF proxy, not spot VIX) | W1 | 13 Jul–17 Jul
| Fear & Greed gauge value (0-100) | P1 | Primary | - | - | Fallback | - | - | - | - | 100% | Polygon | Computed: put/call ratio (Polygon) + market breadth (Polygon) + yields (Finnhub). | Not yet built (in scope, no job written) | Live in UI | Explicit "not wired" placeholder - no backend computation exists | W2 | 20 Jul–24 Jul
| Market Movers Widget — Top Winners | P0 | Primary | - | - | - | - | - | - | - | 100% | Polygon | Polygon /v2/snapshot/locale/us/markets/gainers. | Done (EOD) | Live in UI | Dashboard Market Movers card reads market_movers gainers | W1 | 13 Jul–17 Jul
| Market Movers Widget — Top Losers | P0 | Primary | - | - | - | - | - | - | - | 100% | Polygon | Polygon /v2/snapshot/locale/us/markets/losers. | Done (EOD) | Live in UI | Not shown as a separate widget on Dashboard; full gainers+losers list is live on the Movers screen (/menu/movers) | W1 | 13 Jul–17 Jul
| Market Movers Widget — sector & cap filter | P0 | - | Primary | - | - | - | - | - | - | 100% | FMP | FMP /profile/{sym} for sector + marketCap grouping. | Done (EOD) | Live in UI | Dashboard shows a "Sector Performance" widget (sectors collection) instead of a sector/cap filter on the movers list | W1 | 13 Jul–17 Jul
| Trending Stocks widget (movers x analyst x earnings) | P0 | Primary | Fallback | Fallback | - | - | - | - | - | 100% | Polygon | Server-side: Polygon movers x Benzinga analyst x FMP earnings combined. | Done (EOD) | Dropped (no real data source, faking rejected) | Trending-across-reports widget removed in the Dashboard rewrite (cross-referenced multiple still-mock sources) | W10 | 14 Sep–18 Sep
| Upcoming Earnings list (next 5 days) | P0 | - | Primary | - | Fallback | - | - | - | - | 100% | FMP | FMP /earning_calendar?from=&to=. Finnhub as secondary fallback. | Done (EOD) | Live in UI | Dashboard "Upcoming Earnings" reads earnings_events | W1 | 13 Jul–17 Jul
| Analyst Actions mini-list | P1 | - | Fallback | Primary | - | - | - | - | - | 100% | Benzinga | Benzinga real-time analyst ratings stream. FMP for historical list. | Blocked - no API key | Live in UI | Explicit "not wired" placeholder - needs Benzinga (no key) | W1 | 13 Jul–17 Jul
| Portfolio Snapshot (total value, day P&L) | P0 | Primary | - | - | - | - | - | - | - | 100% | Polygon | Polygon live prices x Firestore holdings cost basis. | Not yet built (in scope, no job written) | Live in UI | Dashboard mini-widget not wired (placeholder), but the full Portfolio screen (/menu/portfolio) is fully live with real Firestore holdings | W1 | 13 Jul–17 Jul
>> EARNINGS HUB
| Earnings calendar rows (ticker, report time, sector) | P0 | - | Primary | Fallback | - | - | - | - | - | 100% | FMP | FMP /earning_calendar. Benzinga real-time stream for actuals as they post. | Done (EOD) | Not wired yet (screen not migrated) | earnings.tsx not migrated this session - deferred (real earnings_events data exists and is ready to wire) | W10 | 14 Sep–18 Sep
| EPS estimate + EPS actual | P0 | - | Primary | Fallback | - | - | - | - | - | 100% | FMP | FMP /historical/earning_calendar/{sym}. Benzinga posts actuals faster. | Done (EOD) | Live in UI | same as row 22 | W1 | 13 Jul–17 Jul
| EPS surprise % | P0 | - | Primary | Fallback | - | - | - | - | - | 100% | FMP | FMP /earnings_surprises/{sym}. Benzinga supplement. | Done (EOD) | Live in UI | same as row 22 | W1 | 13 Jul–17 Jul
| Revenue estimate + actual + surprise % | P0 | - | Primary | - | - | - | - | - | - | 100% | FMP | FMP /income-statement/{sym} + /earning_calendar fields. | Done (EOD) | Not wired yet (screen not migrated) | same as row 22 | W4 | 03 Aug–07 Aug
| Guidance status (raised / lowered / inline) | P0 | - | Primary | Fallback | - | - | - | - | - | 100% | FMP | FMP earnings fields + Benzinga transcript parsing for guidance language. | Done (EOD) | Not wired yet (screen not migrated) | same as row 22 | W8 | 31 Aug–04 Sep
| Tag pills (Beat EPS, Miss Rev, Raises Guide, etc.) | P0 | - | Primary | Fallback | - | - | - | - | - | 100% | FMP | Computed from FMP actuals vs estimates. Benzinga for Large Move + Options Active. | Done (EOD) | Not wired yet (screen not migrated) | same as row 22 | W8 | 31 Aug–04 Sep
| Post-earnings price reaction % | P0 | Primary | - | - | - | - | - | - | - | 100% | Polygon | Polygon /v2/aggs pre/post-event OHLCV comparison. | Not yet built (in scope, no job written) | Not wired yet (screen not migrated) | same as row 22 | W8 | 31 Aug–04 Sep
| 10-quarter EPS history chart | P0 | - | Primary | - | - | - | - | - | - | 100% | FMP | FMP /historical/earning_calendar/{sym} — 10 quarters. | Done (EOD) | Not wired yet (screen not migrated) | The chart shown today is algorithmically-fabricated fake financials - flagged, not just unwired | W4 | 03 Aug–07 Aug
| Real-time earnings actuals (as they drop post-close) | P0 | - | Fallback | Primary | - | - | - | - | - | 100% | Benzinga | Benzinga WS posts within minutes. FMP lags ~10-15min. | Blocked - no API key | Blocked (unchanged - vendor/key missing) | unchanged - needs Benzinga | W8 | 31 Aug–04 Sep
| Earnings call transcript | P1 | - | Primary | Fallback | - | - | - | - | - | 100% | FMP | FMP transcripts on paid plan. Benzinga as fallback source. | Done (EOD) | Not wired yet (screen not migrated) | The call summary/transcript content is fully fabricated fake company text - needs Claude, flagged not just unwired | W4 | 03 Aug–07 Aug
| AI earnings summary (What happened / Beat-miss / Guidance) | P1 | - | Fallback | Fallback | - | - | - | - | Primary | 100% | Claude API | Claude API ingests FMP/Benzinga transcript + key metrics. | Pending Wave 2 - needs ANTHROPIC_API_KEY | Not wired yet (screen not migrated) | needs Claude | W7 | 24 Aug–28 Aug
>> MARKET MOVERS
| Top Gainers (symbol, change%, volume) | P0 | Primary | - | - | - | - | - | - | - | 100% | Polygon | Polygon /v2/snapshot/locale/us/markets/gainers. | Done (EOD) | Live in UI | movers.tsx reads market_movers | W1 | 13 Jul–17 Jul
| Top Losers | P0 | Primary | - | - | - | - | - | - | - | 100% | Polygon | Polygon /v2/snapshot/locale/us/markets/losers. | Done (EOD) | Live in UI | movers.tsx reads market_movers | W1 | 13 Jul–17 Jul
| Unusual Volume view | P0 | Primary | - | - | - | - | - | - | - | 100% | Polygon | Polygon current volume vs 30-day average from /v2/aggs. | Done (EOD) | Live in UI | Renamed "Most Active" - sorted by real volume (no true RVOL baseline available) | W1 | 13 Jul–17 Jul
| Gap Ups / Gap Downs | P0 | Primary | - | - | - | - | - | - | - | 100% | Polygon | Polygon prev-close vs today-open comparison. | Done (EOD) | Dropped (no real data source, faking rejected) | No gap-up/down computation built | W10 | 14 Sep–18 Sep
| High Relative Volume (RVol) | P0 | Primary | - | - | - | - | - | - | - | 100% | Polygon | Polygon today volume / 30-day avg volume. | Done (EOD) | Live in UI | No 30-day average volume computed - would need a new backend job for a real RVOL | W1 | 13 Jul–17 Jul
| Catalyst labels (earnings/analyst/news/macro) | P1 | - | Fallback | Primary | Fallback | - | - | - | - | 100% | Benzinga | Benzinga category-tagged news. FMP earnings flags. Finnhub macro events. | Blocked - no API key | Blocked (unchanged - vendor/key missing) | unchanged - needs Benzinga | W4 | 03 Aug–07 Aug
| Weekly Movers tab (5-day performance) | P1 | Primary | - | - | - | - | - | - | - | 100% | Polygon | Polygon /v2/aggs/ticker/{sym}/range with 5-day window. | Done (EOD) | Dropped (no real data source, faking rejected) | No 5-day historical movers job built | W10 | 14 Sep–18 Sep
| Sector & cap filter metadata | P1 | - | Primary | - | - | - | - | - | - | 100% | FMP | FMP /profile/{sym} for sector + industry + market cap. | Done (EOD) | Live in UI | movers.tsx sector/cap filter dropdowns read companies-derived sector + computed cap bucket | W1 | 13 Jul–17 Jul
>> MARKET HEATMAP
| Sector performance % change | P0 | Primary | Fallback | - | - | - | - | - | - | 100% | Polygon | Polygon sector aggregates. FMP sector list for grouping. | Not yet built (in scope, no job written) | Live in UI | heatmap.tsx reads sectors collection | W1 | 13 Jul–17 Jul
| Stock tiles (symbol, change%, market cap sizing) | P0 | Primary | Fallback | - | - | - | - | - | - | 100% | Polygon | Polygon quotes; FMP for market cap sizing. | Not yet built (in scope, no job written) | Live in UI | heatmap.tsx treemap tiles read companies (sparse: 12/230 tickers synced so far, grows nightly) | W1 | 13 Jul–17 Jul
| Sector summary table (best/worst/avg) | P0 | Primary | Fallback | - | - | - | - | - | - | 100% | Polygon | Computed from Polygon sector aggregates + FMP metadata. | Not yet built (in scope, no job written) | Live in UI | Per-sector header bar shown in heatmap.tsx | W1 | 13 Jul–17 Jul
>> ANALYST ACTIONS
| Upgrade/downgrade/initiation/reiteration rows | P0 | - | Fallback | Primary | - | - | - | - | - | 100% | Benzinga | Benzinga /analyst-ratings stream. FMP historical list. | Blocked - no API key | Not wired yet (screen not migrated) | analyst.tsx not migrated - real analyst_actions data is only a consensus snapshot, not individual dated actions; Benzinga needed for the real shape | W8 | 31 Aug–04 Sep
| Previous rating -> New rating (direction arrow) | P0 | - | Fallback | Primary | - | - | - | - | - | 100% | Benzinga | Benzinga analyst ratings endpoint fields. | Blocked - no API key | Not wired yet (screen not migrated) | same as row 47 | W8 | 31 Aug–04 Sep
| Previous PT -> New price target | P0 | - | Fallback | Primary | - | - | - | - | - | 100% | Benzinga | Benzinga analyst ratings stream fields. | Blocked - no API key | Not wired yet (screen not migrated) | same as row 47 | W8 | 31 Aug–04 Sep
| Implied upside / downside vs current price | P0 | Primary | - | Fallback | - | - | - | - | - | 100% | Polygon | Live price: Polygon. Price target: Benzinga. Formula: (PT - Price)/Price. | Not yet built (in scope, no job written) | Not wired yet (screen not migrated) | same as row 47 | W8 | 31 Aug–04 Sep
| Stock reaction since analyst action date | P1 | Primary | - | - | - | - | - | - | - | 100% | Polygon | Polygon /v2/aggs: price on action date vs today. | Not yet built (in scope, no job written) | Not wired yet (screen not migrated) | same as row 47 | W8 | 31 Aug–04 Sep
| AI note per action (1-line meaningfulness read) | P1 | - | - | - | - | - | - | - | Primary | 100% | Claude API | Claude API: 1-line context per action using Benzinga + Polygon reaction. | Pending Wave 2 - needs ANTHROPIC_API_KEY | Not wired yet (screen not migrated) | needs Claude | W7 | 24 Aug–28 Aug
| Portfolio/watchlist filter overlay | P1 | Live (Firebase) | - | - | - | - | - | - | - | 80% | Firebase (live) | Already live — Firestore portfolio/watchlist; filter client-side. | Already Live (Firebase, pre-existing) | Already Live (unchanged, pre-existing Firebase) | unrelated pre-existing Firebase feature, unchanged | W1 | 13 Jul–17 Jul
>> SECTOR THEMES
| Theme list (8 sector themes: AI, Energy, Biotech, etc.) | P0 | - | Primary | - | - | - | - | - | - | 100% | FMP | FMP /sector list or curated static mapping. Sectors: AI & Chips, Clean Energy, Biotech, FinTech, Defence, Consumer, REITs, Commodities. | Done (EOD) | Partial - see notes | Theme->ticker membership kept as curated editorial config (like screener presets), not vendor data | W4 | 03 Aug–07 Aug
| Stock rows per theme (symbol, price, change%, YTD) | P0 | Primary | Fallback | - | - | - | - | - | - | 100% | Polygon | Polygon batch quotes for each theme's stock list. FMP for YTD return. | Not yet built (in scope, no job written) | Live in UI | themes.tsx reads companies for live price/%change | W1 | 13 Jul–17 Jul
| Selected theme stock list (5-10 stocks per theme) | P0 | Primary | Fallback | - | - | - | - | - | - | 100% | Polygon | Polygon live quotes. FMP /profile for fundamentals filter. | Not yet built (in scope, no job written) | Live in UI | same as row 56 | W1 | 13 Jul–17 Jul
| OHLCV chart (CandleChart per selected stock) | P0 | Primary | - | - | - | - | - | - | - | 100% | Polygon | Polygon /v2/aggs/ticker/{sym}/range — same as Stock Detail chart. | Done (EOD) | Live in UI | Chart component unchanged this session (pre-existing) | W1 | 13 Jul–17 Jul
| Stock detail panel per theme stock (StockScreenEmbed) | P0 | Primary | Fallback | Fallback | - | - | - | Fallback | - | 100% | Polygon | Polygon (quote + chart), FMP (fundamentals), Benzinga (news), SEC EDGAR (insider). Same as Stock Detail screen. | Not yet built (in scope, no job written) | Not wired yet (screen not migrated) | Uses stock.tsx (not migrated) for the per-stock detail panel | W4 | 03 Aug–07 Aug
| Theme performance % (best/worst stock in theme, theme avg) | P1 | Primary | Fallback | - | - | - | - | - | - | 100% | Polygon | Polygon snapshots for all theme symbols. FMP for theme avg calculation. | Not yet built (in scope, no job written) | Live in UI | Computed live from synced companies data | W1 | 13 Jul–17 Jul
| Theme news feed (news filtered by theme symbols) | P1 | - | - | Primary | Fallback | - | - | - | - | 100% | Benzinga | Benzinga /news filtered to symbols in active theme. Finnhub fallback. | Blocked - no API key | Dropped (no real data source, faking rejected) | No per-theme news filtering built | W10 | 14 Sep–18 Sep
| AI theme summary (1-line read per theme) | P2 | - | - | Fallback | - | - | - | - | Primary | 100% | Claude API | Claude API generates 1-line outlook per theme using Benzinga news + Polygon momentum. Phase 2 feature. | Pending Wave 2 - needs ANTHROPIC_API_KEY | Live in UI (relabeled, not AI) | Renamed "Theme snapshot" - real computed stats, not an AI narrative | W7 | 24 Aug–28 Aug
>> SCREENER
| Stock universe (all US equities) | P0 | Primary | Fallback | - | - | - | - | - | - | 100% | Polygon | Polygon /v3/reference/tickers — full US universe. | Done - RS Rating now computed via rs-rating.job.ts (independent IBD-style approximation, not the literal proprietary formula), ranked 1-99 within the curated 241-ticker universe from real ohlcv_bars history; writes nothing until stock-history.job.ts has accumulated enough real bars first (by design, not a bug) | Live in UI — Screener's RS filter buttons (90+/70-90/<40) and RS sparkline label now show the real rsRating value when available, falling back to the mock value otherwise (app/iq/screens/screener.tsx) | screener.tsx not migrated - needs a relative-strength ranking algorithm + growth metrics; no backend job computes these (new engineering, not just wiring) | W2 | 20 Jul–24 Jul
| Fundamental filters (P/E, EPS growth, dividend yield) | P0 | - | Primary | - | - | - | - | - | - | 100% | FMP | FMP /financial-ratios-ttm/{sym} + /income-statement. | Done (EOD) | Live in UI | same as row 64 | W2 | 20 Jul–24 Jul
| Technical filters (MA posture, RSI, volume trend) | P0 | Primary | - | - | - | - | - | - | - | 100% | Polygon | Polygon OHLCV; indicators computed server-side. | Done (EOD) | Live in UI | same as row 64. Prerequisite data now exists: stock-history.job.ts (Polygon EOD aggregates) backfills ~300 days OHLCV for curated TICKER_UNIVERSE (~242 tickers), verified 2026-07-07. However RS Rating / growth-score ranking computation itself is a separate percentile/ranking job that has NOT been built yet - this job only stores raw historical bars. | W2 | 20 Jul–24 Jul
| Sector / industry group classification | P0 | - | Primary | - | - | - | - | - | - | 100% | FMP | FMP /profile/{sym} sector + industry group. | Done (EOD) | Not wired yet (screen not migrated) | companies has real sector field, but screener.tsx not migrated | W4 | 03 Aug–07 Aug
| Market cap bucket (Micro/Small/Mid/Large/Mega) | P0 | Primary | Fallback | - | - | - | - | - | - | 100% | Polygon | Polygon reference + FMP /profile marketCap. | Not yet built (in scope, no job written) | Not wired yet (screen not migrated) | same as row 64 | W4 | 03 Aug–07 Aug
| Named presets (20 presets: value/growth/momentum etc) | P1 | - | Primary | - | - | - | - | - | - | 100% | FMP | Preset filter maps run against FMP fundamentals + Polygon technicals. | Done (EOD) | Partial - see notes | Presets are app configuration (like theme membership), not vendor data - fine to stay static; the numbers they filter over still need rows 64-68 fixed | W4 | 03 Aug–07 Aug
>> IPOs
| Upcoming IPO calendar (company, date, sector, size) | P0 | - | Primary | - | - | - | - | Fallback | - | 100% | Finnhub | FMP /ipo_calendar. SEC EDGAR S-1 filing dates as supplement. | Partially done - IPO calendar (recent + pipeline dates, symbol, exchange, price, status) now live via Finnhub /calendar/ipo (ipos.job.ts); current trading price and day-1 return for newly-public tickers still not available from any vendor for this screen | Live (new additive 'Live IPO Calendar' card in ipos.tsx — separate from, doesn't touch, the original Recent IPO Performance / Upcoming Pipeline tables) | FMP ipos-calendar still confirmed Restricted on current plan, but Finnhub's /calendar/ipo is a separate endpoint, verified live 2026-07-07 via a real test call returning real IPO data (not assumed) | W1 | 13 Jul–17 Jul
| Recent IPO performance (Day-1, since-IPO return) | P0 | Primary | - | - | - | - | - | - | - | 100% | Polygon | Polygon OHLCV: first-day open vs offer price vs current. | Not yet built (in scope, no job written) | Not wired yet (screen not migrated) | no backend job built | W4 | 03 Aug–07 Aug
| IPO offer price | P0 | - | Primary | - | - | - | - | Fallback | - | 100% | Finnhub | FMP /ipo_calendar includes offer price. SEC EDGAR S-1 for precise price. | Partially done - IPO calendar (recent + pipeline dates, symbol, exchange, price, status) now live via Finnhub /calendar/ipo (ipos.job.ts); current trading price and day-1 return for newly-public tickers still not available from any vendor for this screen | Live (new additive 'Live IPO Calendar' card in ipos.tsx — separate from, doesn't touch, the original Recent IPO Performance / Upcoming Pipeline tables) | FMP ipos-calendar still confirmed Restricted on current plan, but Finnhub's /calendar/ipo is a separate endpoint, verified live 2026-07-07 via a real test call returning real IPO data (not assumed) | W1 | 13 Jul–17 Jul
| Above/below offer count + median return stats | P1 | Primary | Fallback | - | - | - | - | - | - | 100% | Polygon | Computed from Polygon current prices vs FMP offer prices. | Not yet built (in scope, no job written) | Not wired yet (screen not migrated) | no backend job built | W4 | 03 Aug–07 Aug
>> STOCK DETAIL
| Real-time quote (price, change, volume, VWAP) | P0 | Primary | - | - | - | - | - | - | - | 100% | Polygon | Polygon /v2/snapshot/locale/us/markets/ticker/{sym}. | Done (EOD) | Live in UI | stock.tsx not migrated this session - companies has real price data, ready to wire | W2 | 20 Jul–24 Jul
| OHLCV chart data (1D/1W/1M/3M/6M/1Y/5Y) | P0 | Primary | - | - | - | - | - | - | - | 100% | Polygon | Polygon /v2/aggs/ticker/{sym}/range with interval + timespan. Update 2026-07-09: deployed a Firestore composite index (ticker + barDate) on ohlcv_bars via a new firestore.indexes.json, fixing a FAILED_PRECONDITION error that was blocking stock-history.job.ts. | Done - live via Polygon EOD aggregates (stock-history.job.ts), backfills ~300 trading days OHLCV per ticker for curated TICKER_UNIVERSE (~242 tickers), incremental daily fetch via per-ticker watermark. Feeds real chart data for 3M/6M/1Y only; 1D/1W (needs intraday, not stored) and 5Y (needs more history than 300-day backfill) still fall back to simulated generator. | Live in UI | Verified 2026-07-07: stock-history.job.ts confirmed working on Polygon free plan. Stock Detail chart now real for 3M/6M/1Y timeframes; 1D/1W/5Y remain simulated. | W2 | 20 Jul–24 Jul
| Company fundamentals (PE, EPS, revenue, market cap, beta) | P0 | Fallback | Primary | - | Fallback | - | - | - | - | 100% | FMP | FMP /key-metrics-ttm/{sym}. Polygon + Finnhub as fallback. | Done (EOD) | Live in UI | companies has real fundamentals (PE, EPS, marketCap, beta) - ready to wire | W2 | 20 Jul–24 Jul
| Sector / industry group rank | P0 | - | Primary | - | - | - | - | - | - | 100% | FMP | FMP /profile/{sym} + FMP industry rank endpoint. | Done (EOD) | Live in UI | companies has real sector field - ready to wire | W2 | 20 Jul–24 Jul
| Analyst rating consensus (Buy/Neutral/Sell counts) | P0 | - | Primary | Fallback | - | - | - | - | - | 100% | FMP | FMP /analyst-stock-recommendations/{sym}. Benzinga for latest. | Done (EOD) | Not wired yet (screen not migrated) | analyst_actions has interim consensus shape but is currently empty (FMP quota exhausted) | W3 | 27 Jul–31 Jul
| 10-quarter EPS history chart | P0 | - | Primary | - | - | - | - | - | - | 100% | FMP | FMP /historical/earning_calendar/{sym}. | Done (EOD) | Not wired yet (screen not migrated) | Chart shown today is fabricated fake financials, same concern as row 29 | W3 | 27 Jul–31 Jul
| Recent news (last 24-48h) | P0 | Primary | - | - | Fallback | - | - | - | - | 100% | Polygon (primary) + Finnhub (fallback) | Polygon /v2/reference/news?ticker={sym} primary (adds per-ticker sentiment, sentimentReasoning, keywords). Finnhub /company-news automatic fallback. Benzinga still required for per-firm category tagging (blocked, no key). | Done | Not wired yet (screen not migrated) | news collection has real data, ready to wire | W3 | 27 Jul–31 Jul
| 52-week high/low, float, short interest | P0 | Primary | Fallback | - | - | - | - | - | - | 100% | Polygon | Polygon /v3/reference/tickers/{sym}. FMP /key-metrics. | Done (EOD) | Not wired yet (screen not migrated) | companies has real week52Range field - ready to wire | W3 | 27 Jul–31 Jul
| Insider activity (Form 4 transactions) | P1 | - | - | - | - | - | - | Primary | - | 100% | SEC EDGAR | SEC EDGAR Form 4 XML. Batch nightly. Rate limit 10 req/sec. | Done (EOD) | Not wired yet (screen not migrated) | insider_transactions has real data, filterable by ticker - ready to wire | W3 | 27 Jul–31 Jul
| Institutional ownership (top 10 holders) | P1 | - | Primary | - | - | - | - | Fallback | - | 100% | FMP | FMP /institutional-holder/{sym}. SEC EDGAR 13F supplement. | Done (EOD) | Not wired yet (screen not migrated) | fund_holdings has real data - ready to wire | W3 | 27 Jul–31 Jul
| Options activity flags (unusual OI/volume) | P2 | - | - | - | - | Fallback | Primary | - | - | 100% | Univ.Whales | Unusual Whales detection. Tradier chain for OI/volume context. | Blocked - no API key | Blocked (unchanged - vendor/key missing) | unchanged - needs Unusual Whales | W9 | 07 Sep–11 Sep
| AI technical analysis (4 tone modes) | P1 | - | - | - | - | - | - | - | Primary | 100% | Claude API | Claude API with OHLCV + indicators context. Phase 2 feature. | Pending Wave 2 - needs ANTHROPIC_API_KEY | Not wired yet (screen not migrated) | needs Claude | W7 | 24 Aug–28 Aug
| AI thesis + risk + confidence score | P1 | - | Fallback | Fallback | - | - | - | - | Primary | 100% | Claude API | Claude API ingests Benzinga news + FMP fundamentals. | Pending Wave 2 - needs ANTHROPIC_API_KEY | Not wired yet (screen not migrated) | needs Claude | W7 | 24 Aug–28 Aug
| Stock chart notes (save/load/delete) | P0 | Live (Firebase) | - | - | - | - | - | - | - | 80% | Firebase (live) | Already live — Firestore stock_comments collection. | Already Live (Firebase, pre-existing) | Already Live (unchanged, pre-existing Firebase) | stock_comments - unchanged, was already live before this whole project started | W2 | 20 Jul–24 Jul
| Peers list (5-10 peers by sector/model) | P1 | - | Primary | - | - | - | - | - | - | 100% | FMP | FMP /stock-peers/{sym} endpoint. | Done (EOD) | Not wired yet (screen not migrated) | companies has real peers array - ready to wire | W3 | 27 Jul–31 Jul
>> OPTIONS CHAIN
| Options chain (strike, bid, ask, IV%, OI, volume) | P0 | - | - | - | - | Primary | Fallback | - | - | 100% | Tradier | Tradier /options/chains — free with brokerage account. | Partially done - strike price + delayed last close/volume now live via Polygon (options-chains.job.ts) for a curated 8-ticker universe; bid, ask, IV%, and OI remain Blocked - no API key (Polygon's options snapshot/quotes confirmed 403 NOT_AUTHORIZED on the current plan, verified 2026-07-07; would need a plan upgrade or Tradier) | Blocked (unchanged - vendor/key missing) | unchanged - needs Tradier | W5 | 10 Aug–14 Aug
| Expiry dates list | P0 | - | - | - | - | Primary | - | - | - | 100% | Polygon | Tradier /options/expirations. | Done - expiration dates now live via Polygon /v3/reference/options/contracts (options-chains.job.ts), for the curated 8-ticker OPTIONS_UNIVERSE (AAPL, MSFT, NVDA, TSLA, AMZN, META, SPY, QQQ) only, not the full ticker universe options.tsx's picker lists | Blocked (unchanged - vendor/key missing) | unchanged - needs Tradier | W5 | 10 Aug–14 Aug
| Greeks (Delta, Gamma, Theta, Vega) | P0 | - | - | - | - | Primary | Fallback | - | - | 100% | Tradier | Tradier options chain includes Greeks. | Blocked - no API key | Blocked (unchanged - vendor/key missing) | unchanged - needs Tradier | W5 | 10 Aug–14 Aug
| Unusual options flow detection | P2 | - | - | - | - | Fallback | Primary | - | - | 100% | Univ.Whales | Unusual Whales API. Phase 2 feature. Not MVP-critical. | Blocked - no API key | Blocked (unchanged - vendor/key missing) | unchanged - needs Unusual Whales | W9 | 07 Sep–11 Sep
| Dark pool prints | P2 | - | - | - | - | - | Primary | - | - | 100% | Univ.Whales | Unusual Whales dark pool data. Phase 2. | Blocked - no API key | Blocked (unchanged - vendor/key missing) | unchanged - needs Unusual Whales | W9 | 07 Sep–11 Sep
>> INSIDER & INSTITUTIONAL
| Form 4 insider transactions (buy/sell, date, value) | P1 | - | - | - | - | - | - | Primary | - | 100% | SEC EDGAR | SEC EDGAR Form 4 XML parsing. Batch overnight. | Done (EOD) | Live in UI | insider.tsx reads insider_transactions - 143 real Form 4 rows synced so far | W1 | 13 Jul–17 Jul
| 13F institutional holdings (fund, ticker, shares, value) | P1 | - | Fallback | - | - | - | - | Primary | - | 100% | SEC EDGAR | SEC EDGAR 13F-HR filings. FMP /institutional-holder supplement. | Done (EOD) | Live in UI | insider.tsx reads fund_holdings/{cik}/filings/{accession}/positions - 102 real positions synced | W1 | 13 Jul–17 Jul
| Fund cards (name, AUM, top holdings) | P1 | - | Primary | - | - | - | - | Fallback | - | 100% | FMP | FMP fund data. SEC EDGAR 13F for exact positions. | Done (EOD) | Live in UI | insider.tsx fund cards read fund_holdings | W1 | 13 Jul–17 Jul
| AI 13F quarterly digest per fund | P2 | - | - | - | - | - | - | Fallback | Primary | 100% | Claude API | Claude API summarizes SEC EDGAR 13F changes. Phase 2. | Pending Wave 2 - needs ANTHROPIC_API_KEY | Not wired yet (screen not migrated) | needs Claude - replaced with a real top-holdings drawer (factual, not AI) instead | W7 | 24 Aug–28 Aug
| Cross-fund views (most owned/sold across funds) | P2 | - | - | - | - | - | - | Primary | - | 100% | SEC EDGAR | Server-side aggregation of SEC EDGAR 13F data. | Done (EOD) | Live in UI (relabeled, not AI) | Real cross-fund overlap computed by matching CUSIP across all 5 tracked funds' actual positions - exact, not an estimate. Improves on the original AI-digest concept. | W1 | 13 Jul–17 Jul
>> PORTFOLIO PULSE
| Live prices for all holdings | P0 | Primary | - | - | - | - | - | - | - | 100% | Polygon | Polygon batch /v2/snapshot for all held symbols. | Not yet built (in scope, no job written) | Live in UI | portfolio.tsx reads companies for live price/%change | W1 | 13 Jul–17 Jul
| Holdings persistence (add/remove/sell) | P0 | Live (Firebase) | - | - | - | - | - | - | - | 80% | Firebase (live) | Partial (localStorage). Full: Firestore users/{uid}/portfolios. | Done | Live in UI | Holdings now persisted to users/{uid}/portfolios/default/holdings in Firestore - upgraded from local-state-only ¦ 2026-07-09: Computed portfolio summary (totalValue, dayPL, dayPLPct, holdingsCount) is now materialized (written, debounced ~3s) onto the parent users/{uid}/portfolios/default Firestore doc by app/iq/screens/portfolio.tsx, in addition to pre-existing per-ticker holdings CRUD. Client-side write only (not a vendor/backend job); the app UI does NOT read this cached value back - it is a side effect for future external consumers (notifications, backend job, historical tracking). | W1 | 13 Jul–17 Jul
| Position P&L (unrealized gain/loss) | P0 | Primary | - | - | - | - | - | - | - | 100% | Polygon | Polygon live price vs Firestore cost basis. | Not yet built (in scope, no job written) | Live in UI | Computed live from synced holdings + companies | W1 | 13 Jul–17 Jul
| AI Drivers / Laggards / Leaders summary | P1 | - | - | Fallback | - | - | - | - | Primary | 100% | Claude API | Claude API with portfolio context + Benzinga news per holding. | Pending Wave 2 - needs ANTHROPIC_API_KEY | Live in UI (relabeled, not AI) | Renamed "Portfolio snapshot" - real computed stats (biggest position, leader/laggard, day P&L), not an AI narrative | W7 | 24 Aug–28 Aug
| 12-alert types (earnings/analyst/volume/price) | P0 | Primary | Fallback | Fallback | Fallback | - | - | - | - | 100% | Polygon | Polygon (price/vol), FMP (earnings), Benzinga (analyst/news), Finnhub (macro). | Done (EOD) | Not wired yet (screen not migrated) | Alerts feature not touched this session | W9 | 07 Sep–11 Sep
>> WATCHLIST
| Live prices for watched symbols | P0 | Primary | - | - | - | - | - | - | - | 100% | Polygon | Polygon batch quotes for all watchlist symbols. | Not yet built (in scope, no job written) | Live in UI | watchlist.tsx reads companies for live price/%change | W1 | 13 Jul–17 Jul
| Watchlist persistence (across sessions) | P0 | Live (Firebase) | - | - | - | - | - | - | - | 80% | Firebase (live) | Currently localStorage. Migrate: Firestore users/{uid}/watchlists. | Already Live (Firebase, pre-existing) | Live in UI | Watchlist now persisted to users/{uid}/watchlists/default in Firestore - upgraded from local-state-only | W1 | 13 Jul–17 Jul
| Alert pills (price move, analyst upgrade) | P0 | Primary | - | Fallback | - | - | - | - | - | 100% | Polygon | Polygon for price moves. Benzinga for analyst alerts. | Not yet built (in scope, no job written) | Not wired yet (screen not migrated) | Alerts feature not touched this session | W9 | 07 Sep–11 Sep
| AI alert toggle per stock | P1 | - | - | - | - | - | - | - | Primary | 100% | Claude API | Claude API on-demand: 1-line AI context per enabled stock. | Pending Wave 2 - needs ANTHROPIC_API_KEY | Not wired yet (screen not migrated) | needs Claude | W7 | 24 Aug–28 Aug
| Upside % (current price vs analyst price target) | P0 | Primary | Fallback | Fallback | - | - | - | - | - | 100% | Polygon | Live price: Polygon. Price target: FMP or Benzinga. | Not yet built (in scope, no job written) | Not wired yet (screen not migrated) | Needs analyst price-target data - blocked (Benzinga/FMP quota) | W8 | 31 Aug–04 Sep
>> COMMENTARY / NEWS
| News feed articles (headline, blurb, category tag) | P0 | Primary | - | - | Fallback | - | - | - | - | 100% | Polygon (primary) + Finnhub (fallback) | Polygon /v2/reference/news primary (adds per-ticker sentiment, sentimentReasoning, keywords). Finnhub /company-news automatic fallback. Benzinga still required for per-firm category tagging + real-time push (blocked, no key). | Done | Live in UI | commentary.tsx reads news (Polygon primary w/ sentiment+keywords, Finnhub automatic fallback; Benzinga category tagging still pending - blocked, no key) | W8 | 31 Aug–04 Sep
| Category tags (Catalyst/Technical/Sector/Analyst) | P0 | - | - | Primary | - | - | - | - | - | 100% | Benzinga | Benzinga category field in news API response — pre-tagged. | Blocked - no API key | Live in UI | Using Finnhub's real category field | W8 | 31 Aug–04 Sep
| Ticker search autocomplete | P0 | Primary | - | - | - | - | - | - | - | 100% | Polygon | Polygon /v3/reference/tickers?search={q}. | Not yet built (in scope, no job written) | Live in UI | Built live from synced news tickers | W1 | 13 Jul–17 Jul
| NewsDrawer history items per ticker | P0 | Primary | Fallback | Primary | Fallback | - | - | - | - | 100% | Polygon + Benzinga | Benzinga news + FMP earnings + Polygon price events + Finnhub macro. | Not yet built (in scope, no job written) | Live in UI | Per-ticker drawer reads real synced articles | W1 | 13 Jul–17 Jul
| My names tab (watchlist-linked news feed) | P1 | Live (Firebase) | - | Primary | - | - | - | - | - | 100% | Benzinga | Watchlist from Firestore. News filtered by symbols from Benzinga. | Blocked - no API key | Dropped (no real data source, faking rejected) | "My names" tab removed - depended on still-unmigrated watchlist/portfolio cross-reference at the time; can be re-added now that both are live | W10 | 14 Sep–18 Sep
>> RECAPS (EOD / WEEKLY)
| Index returns data (9 indices) | P0 | Primary | - | - | Fallback | - | - | - | - | 100% | Polygon | Polygon /v2/snapshot for SPX, NDX, DJI, RUT, VIX, etc. | Done (EOD, ETF proxy) | Not wired yet (screen not migrated) | recap.tsx not migrated (market_indices exists and could feed this) | W4 | 03 Aug–07 Aug
| Top stories of the day | P0 | - | - | Primary | Fallback | - | - | - | - | 100% | Benzinga | Benzinga top news ranked by impact. Finnhub fallback. | Blocked - no API key | Blocked (unchanged - vendor/key missing) | unchanged - needs Benzinga | W4 | 03 Aug–07 Aug
| Sector heatmap data | P0 | Primary | Fallback | - | - | - | - | - | - | 100% | Polygon | Polygon sector aggregates. FMP for labels. | Not yet built (in scope, no job written) | Not wired yet (screen not migrated) | recap.tsx not migrated (sectors data exists and could feed this) | W4 | 03 Aug–07 Aug
| Earnings movers (post-print reactions) | P0 | Primary | Fallback | - | - | - | - | - | - | 100% | Polygon | Polygon price data. FMP earnings actuals. | Done (EOD) | Not wired yet (screen not migrated) | recap.tsx not migrated (earnings_events exists but has no post-earnings price-reaction tracking yet) | W4 | 03 Aug–07 Aug
| AI EOD/weekly headline + narrative summary | P0 | - | Fallback | Fallback | - | - | - | - | Primary | 100% | Claude API | Claude API (cron 4:30pm ET) generates summary from structured day data. | Pending Wave 2 - needs ANTHROPIC_API_KEY | Not wired yet (screen not migrated) | needs Claude | W6 | 17 Aug–21 Aug
| Market internals (advance/decline, new highs/lows) | P1 | Primary | - | - | - | - | - | - | - | 100% | Polygon | Polygon /v2/snapshot/locale/us/markets for breadth metrics. | Not yet built (in scope, no job written) | Not wired yet (screen not migrated) | No market breadth (advance/decline) data source exists | W4 | 03 Aug–07 Aug
>> MACRO & VIX
| Economic calendar (CPI, PPI, FOMC, GDP, PCE) | P0 | - | Fallback | - | Primary | - | - | - | - | 100% | FRED | Finnhub /calendar/economic — free on all plans. FMP fallback. | Partially done - CPI/PPI/GDP latest reading live via FRED (macro-events.job.ts); FOMC decision + forward calendar still blocked (FRED has no consensus-estimate/forward-calendar concept) | Live in UI | unchanged - both FMP and Finnhub economic-calendar endpoints confirmed Restricted on current plans | W1 | 13 Jul–17 Jul
| VIX level + day change + 30-day sparkline | P0 | Primary | - | - | Fallback | - | - | - | - | 100% | Polygon | Polygon /v2/snapshot for $VIX. Finnhub fallback. | Done (EOD, ETF proxy) | Partial - see notes | market_indices has a real VIX proxy (VIXY), but macro.tsx itself was not migrated this session - only the Dashboard VIX widget uses it | W4 | 03 Aug–07 Aug
| 10Y yield / 2Y yield / yield curve | P0 | Primary | - | - | Fallback | - | - | - | - | 100% | Polygon | Polygon /v2/snapshot for TNX, IRX bond tickers. | Partially done - 10Y yield (DGS10) now live via FRED; 2Y yield and yield-curve spread still not built | Partial - see notes | market_indices has a real US10Y proxy (TLT), but macro.tsx itself was not migrated this session | W4 | 03 Aug–07 Aug
| Fed funds rate | P0 | - | - | - | Primary | - | - | - | - | 100% | Finnhub | Finnhub /calendar/economic or FRED API (free). | Done - live via FRED (FEDFUNDS series) | Blocked (unchanged - vendor/key missing) | unchanged - Finnhub restricted | W4 | 03 Aug–07 Aug
| Prior / estimate / actual / surprise per event | P0 | - | Fallback | - | Primary | - | - | - | - | 100% | Finnhub | Finnhub economic calendar includes all 4 fields per event. | Partially done - prior/actual live via FRED; estimate/surprise not available (FRED has no consensus-estimate concept) | Blocked (unchanged - vendor/key missing) | unchanged - Finnhub restricted | W4 | 03 Aug–07 Aug
| Market regime label (7 states: Risk-On/Risk-Off etc.) | P1 | Primary | - | - | Fallback | - | - | - | Fallback | 100% | Polygon | Server-side: Polygon VIX + breadth + Finnhub yields + Claude. | Not yet built (in scope, no job written) | Not wired yet (screen not migrated) | No market-regime computation built | W4 | 03 Aug–07 Aug
| Dividend calendar (ex-date, pay date, amount, yield, frequency) | P1 | - | Primary | - | - | - | - | - | - | 10000% | FMP | Real-time ex-dividend calendar across whole market, not just curated tickers | Done - live via FMP /stable/dividends-calendar (dividends.job.ts), verified working 2026-07-07 (not restricted, unlike economic-calendar/ipos-calendar on this same FMP plan) | Live (new additive 'Live Dividend Calendar' card in macro.tsx) | Tested directly with a real API call 2026-07-07 — confirmed 200 OK with real dividend data | W1 | 13 Jul–17 Jul
Shell / Cross-Screen (Cmd+K search) | Full-market ticker price data (price, %change, volume — ~10,000+ US tickers, not just the curated 241-ticker list) | P2 | Primary | - | - | - | - | - | - | - | 100 | Polygon | Reuses the same 2-call grouped-daily diff market-movers.job.ts already computes for the whole market — zero new API calls, zero new vendor key, zero quota risk. Fundamentals (P/E, sector, dividend yield, peers, beta) for the full market are a SEPARATE, NOT-done capability — those need one FMP call per ticker and remain limited to the curated 241-ticker list (see companies collection / row 64's related-but-distinct RS-ranking gap). | Done - live via market-quotes.job.ts, merged onto tickers/{ticker} alongside ticker-universe.job.ts's existing weekly reference metadata (name/exchange/type/cik) | Live in UI — wired to the Cmd+K/top search bar (app/iq/shell.tsx via app/iq/hooks/useTickerSearch.ts), ticker-prefix search only (not company-name search yet). Verified: tsc clean, dev server compiles with zero console/network errors; could not click-test the actual dropdown interaction (behind Firebase auth, no test credentials available). | Built and verified 2026-07-08 — backend tsc/lint/build all clean; schema.sql's tickers table verified against a real isolated Postgres instance with zero errors | W1 | 13 Jul–17 Jul

## Coverage by Screen
StockWise — Coverage Summary by Screen (P0=MVP blocker, P1=high quality, P2=Phase 2)
Screen | Total Data Points | Fully Covered (Primary) | Partial (Fallback/Live) | Not Covered | Coverage % | Primary Vendors | Est. Monthly Cost to Enable | Live in UI Today | % Live Today
SHELL / TICKER STRIP | 4 | 1 | 3 | 0 | 85% | Polygon | Polygon $29 | 4/4 | 100%
DASHBOARD | 11 | 11 | 0 | 0 | 100% | Benzinga, Claude API, FMP, Polygon | Polygon $29 + FMP $99 + Claude API | 9/11 | 81.82%
EARNINGS HUB | 11 | 11 | 0 | 0 | 100% | Benzinga, Claude API, FMP, Polygon | FMP $99 + Benzinga $149-299 | 2/11 | 18.18%
MARKET MOVERS | 8 | 8 | 0 | 0 | 100% | Benzinga, FMP, Polygon | Polygon $29 + Benzinga $149-299 | 5/8 | 62.5%
MARKET HEATMAP | 3 | 3 | 0 | 0 | 100% | Polygon | Polygon $29 | 3/3 | 100%
ANALYST ACTIONS | 7 | 6 | 1 | 0 | 97.14% | Benzinga, Claude API, Polygon | Benzinga $149-299 + Claude API | 1/7 | 14.29%
SECTOR THEMES | 8 | 8 | 0 | 0 | 100% | Benzinga, Claude API, FMP, Polygon | Polygon $29 + FMP $99 | 5/8 | 62.5%
SCREENER | 6 | 6 | 0 | 0 | 100% | FMP, Polygon | Polygon $29 + FMP $99 | 3/6 | 50%
IPOs | 4 | 4 | 0 | 0 | 100% | FMP, Polygon | FMP $99 (SEC EDGAR free) | 2/4 | 50%
STOCK DETAIL | 15 | 14 | 1 | 0 | 98.67% | Benzinga, Claude API, FMP, Polygon, SEC EDGAR, Univ.Whales | Polygon $29 + FMP $99 + Benzinga $149-299 + Claude API | 5/15 | 33.33%
OPTIONS CHAIN | 5 | 5 | 0 | 0 | 100% | Tradier, Univ.Whales | Tradier (Free) | 0/5 | 0%
INSIDER & INSTITUTIONAL | 5 | 5 | 0 | 0 | 100% | Claude API, FMP, SEC EDGAR | SEC EDGAR (Free) | 4/5 | 80%
PORTFOLIO PULSE | 5 | 4 | 1 | 0 | 96% | Claude API, Polygon | Polygon $29 | 4/5 | 80%
WATCHLIST | 5 | 4 | 1 | 0 | 96% | Claude API, Polygon | Polygon $29 | 2/5 | 40%
COMMENTARY / NEWS | 5 | 5 | 0 | 0 | 100% | Benzinga, Polygon | Benzinga $149-299 | 4/5 | 80%
RECAPS (EOD / WEEKLY) | 6 | 6 | 0 | 0 | 100% | Benzinga, Claude API, Polygon | Polygon $29 + Benzinga + Claude API | 0/6 | 0%
MACRO & VIX | 6 | 6 | 0 | 0 | 100% | Finnhub, Polygon | Finnhub (Free) | 2/6 | 33.33%
TOTAL / OVERALL | 114 | 107 | 7 | 0 | 98.77% | Full stack | ~$325-475/mo | 55/114 | 48.25%
% Live Today re-verified 2026-07-12 vs app/iq/screens + backend/src/sync + Doc/screen-data-sources.md. 'Live' = real (non-mock) data shown in the UI, incl. hybrid overlays. Newly live since 2026-07-04: Stock Detail live quote/fundamentals + 3M/6M/1Y candles (index-query fix); Screener RS Rating; IPO + dividend + macro-indicator live cards; Dashboard movers/earnings/portfolio hybrids; Themes per-stock candles. (Separate 2026-07-12 backend migration to Polygon changed data SOURCES only, not the live count.) ¦ 2026-07-12 part 2: computed indicator/score jobs (technical-indicators, tech-rating, fundamentals-growth, fear-greed) turned RSI/MACD, RVOL, Tech Rating, sector rank, sales/EPS growth, gross margin, and Fear & Greed from 'no source' into code-complete+wired (live once the jobs run) — +5 data points.

## Cost Optimizer
StockWise — Cost-Optimized Vendor Combos to Reach ~100% Coverage
Combo / Stage | Vendor Stack | Monthly Cost | Coverage % | What Gets Unlocked | Gaps / Trade-offs
1. Budget Starter (Internal alpha / dev) | Polygon.io + FMP + Finnhub (free) + SEC EDGAR (free) + Tradier (free) | $128/mo | 68% | Dashboard, Movers, Heatmap, Earnings (core), Screener, IPOs, Stock Detail (no news/analyst), Options Chain, Insider/13F, Portfolio, Watchlist, Macro | No real-time news feed No analyst actions board No AI features No Benzinga = no Why It Moves Enough for dev/internal alpha only
2. MVP Minimum (Closed beta — Week 6) | Polygon.io + FMP + Benzinga + Finnhub (free) + SEC EDGAR (free) + Tradier (free) | $277-399/mo | 92% | All above + Analyst Actions board (live) + Commentary/news feed + Stock Detail with news + Dashboard WMN context + Earnings actuals real-time | No AI features yet Unusual options flow excluded (Phase 2) 100% of P0 MVP features covered All In Progress screens functional
3. MVP Recommended (Public launch — Week 22) | Polygon.io + FMP + Benzinga + Finnhub (free) + Tradier (free) + SEC EDGAR (free) + Claude API | $300-430/mo | 97% | All above + AI earnings summaries + AI analyst notes + Dashboard WMN AI card + AI portfolio summary (Drivers/Laggards) + AI EOD/weekly recaps | Unusual Whales excluded (Phase 2) ~97% of all P0+P1 features live AI differentiates from competitors Viable for Pro tier subscribers
4. Phase 2 Complete (Premium tier — Week 38) | All above + Unusual Whales ($48/mo) | $348-478/mo | 100% | All screens + Unusual options flow + Dark pool prints + Congressional trades + AI Market Copilot + AI TA analysis + Phase 2 full feature set | 100% feature parity Full Premium tier justified Consider Intrinio ($250/mo) only if FMP transcripts insufficient
RECOMMENDATION: Start Combo 1 for dev/alpha, Combo 2 for closed beta (Week 6), launch with Combo 3 (Week 22), add Unusual Whales for Phase 2.
LEGEND: | Primary | Fallback | Live (Firebase) | Not covered | P0 = MVP Blocker

## Delivery Plan (W1-W10)
MarketCatalyst — 10-Week Delivery Plan (development + testing)
Start Mon 13 Jul 2026 → finish Fri 18 Sep 2026. Person-days for a small team; each week (Mon-Fri) is independently shippable. W1-W4 need NO new keys.
Week | Start | End | Screen | Deliverable (dev + test) | Dependency | Dev (d) | Test (d) | Total (d) | Priority | Cum (d)
W1 | 13 Jul | 17 Jul | Infra / All | Firestore→Blaze, service-account.json, deploy backend 24/7 | Infra | 2 | 1 | 3 | P0 | 3
W1 | 13 Jul | 17 Jul | Infra / All | Deploy Firestore composite indexes + TTL purge policies | Infra | 1 | 0.5 | 1.5 | P0 | 4.5
W1 | 13 Jul | 17 Jul | Ops | Run all data jobs; verify sync_meta + ops dashboard | Infra | 1 | 1 | 2 | P0 | 6.5
W1 | 13 Jul | 17 Jul | Dashboard | Go-live verify: pulse, VIX, movers/earnings/portfolio/watch/analyst minis | Key: Polygon-paid | 1 | 1 | 2 | P0 | 8.5
W1 | 13 Jul | 17 Jul | Market Movers | Go-live verify: gainers/losers/unusual-vol/RVol/filter | Key: Polygon-paid | 0.5 | 1 | 1.5 | P0 | 10
W1 | 13 Jul | 17 Jul | Market Heatmap | Go-live verify: sector %, tiles, summary | Key: Polygon-paid | 0.5 | 0.5 | 1 | P0 | 11
W1 | 13 Jul | 17 Jul | Macro & VIX | Go-live verify: economic calendar + dividend + full-market | Key: Polygon-paid | 0.5 | 0.5 | 1 | P0 | 12
W1 | 13 Jul | 17 Jul | IPOs | Go-live verify: IPO calendar + offer price | Key: Polygon-paid | 0.5 | 0.5 | 1 | P0 | 13
W1 | 13 Jul | 17 Jul | Commentary / News | Go-live verify: feed/tags/search/drawer + multi-source aggregation | Key: Polygon-paid | 1 | 1 | 2 | P0 | 15
W1 | 13 Jul | 17 Jul | Sector Themes | Go-live verify: theme stock rows/list/candle/perf/AI summary | Key: Polygon-paid | 0.5 | 0.5 | 1 | P1 | 16
Firebase account creation, Polygon subsrition and API, API data verification, Backend API creation , Initial project setup
W2 | 20 Jul | 24 Jul | Stock Detail | Backfill ohlcv_bars (stock-history) across full universe | Key: Polygon-paid | 1 | 0.5 | 1.5 | P0 | 17.5
W2 | 20 Jul | 24 Jul | All scores | Run compute jobs: rs-rating, technical-indicators, tech-rating, fundamentals-growth, fear-greed | Key: Polygon-paid | 0.5 | 1 | 1.5 | P0 | 19
W2 | 20 Jul | 24 Jul | Stock Detail | Verify quote/fundamentals/3M-6M-1Y chart/RSI-MACD/sector rank | Key: Polygon-paid | 0.5 | 1.5 | 2 | P0 | 21
W2 | 20 Jul | 24 Jul | Screener | Verify universe + fundamental/technical filters + Tech Rating/RVOL/growth/margin | Key: Polygon-paid | 0.5 | 1.5 | 2 | P0 | 23
W2 | 20 Jul | 24 Jul | Dashboard | Fear & Greed gauge — verify live | Key: Polygon-paid | 0.5 | 0.5 | 1 | P1 | 24
W2 | 20 Jul | 24 Jul | Shell / Search | Ticker-universe re-run to backfill nameLower/searchTokens; verify company-name search | Key: Polygon-paid | 0.5 | 0.5 | 1 | P1 | 25
W3 | 27 Jul | 31 Jul | Stock Detail | Wire live analyst consensus (from analyst_actions) | Key: Polygon-paid | 1 | 0.5 | 1.5 | P0 | 26.5
W3 | 27 Jul | 31 Jul | Stock Detail | 52-week high/low + float (compute from ohlcv_bars) | Key: Polygon-paid | 1.5 | 0.5 | 2 | P0 | 28.5
W3 | 27 Jul | 31 Jul | Stock Detail | 10-quarter EPS history chart (Polygon financials) | Key: Polygon-paid | 1.5 | 0.5 | 2 | P0 | 30.5
W3 | 27 Jul | 31 Jul | Stock Detail | Wire real recent-news (replace mock, from news collection) | Key: Polygon-paid | 1 | 0.5 | 1.5 | P0 | 32
W3 | 27 Jul | 31 Jul | Stock Detail | Wire real insider activity (from insider_transactions) | Key: Polygon-paid | 1 | 0.5 | 1.5 | P1 | 33.5
W3 | 27 Jul | 31 Jul | Portfolio / Watchlist | Real-holdings + AI-summary verification | Key: Polygon-paid | 0.5 | 1 | 1.5 | P0 | 35
W4 | 03 Aug | 07 Aug | Recaps | EOD recap data job: index returns, sector heatmap, earnings movers, internals | Key: Polygon-paid | 3 | 1 | 4 | P0 | 39
W4 | 03 Aug | 07 Aug | Screener | Sector/industry classification + market-cap bucket (from companies) | Key: Polygon-paid | 1 | 0.5 | 1.5 | P0 | 40.5
W4 | 03 Aug | 07 Aug | IPOs | Recent IPO performance + above/below-offer stats (compute) | Key: Polygon-paid | 1.5 | 0.5 | 2 | P0 | 42.5
W4 | 03 Aug | 07 Aug | Macro & VIX | VIX + 10Y/2Y yields + Fed funds + market-regime label (FRED + compute) | Key: Polygon-paid | 2 | 1 | 3 | P0 | 45.5
W5 | 10 Aug | 14 Aug | Options Chain | Procure Tradier token / Polygon Options plan | Key: Tradier/Polygon | 0.5 | 0 | 0.5 | P0 | 46
W5 | 10 Aug | 14 Aug | Options Chain | Build/finish options adapter: bid/ask, IV, OI, Greeks | Key | 3 | 1 | 4 | P0 | 50
W5 | 10 Aug | 14 Aug | Options Chain | Wire full chain + expiry list + Greeks into Options screen | Key | 2 | 1.5 | 3.5 | P0 | 53.5
W6 | 17 Aug | 21 Aug | AI / All | Procure ANTHROPIC_API_KEY; build AI service + prompt/caching infra | Key: Claude | 2 | 0.5 | 2.5 | P0 | 56
W6 | 17 Aug | 21 Aug | Recaps | AI EOD/weekly narrative (headline + summary) | Key: Claude | 2 | 1 | 3 | P0 | 59
W6 | 17 Aug | 21 Aug | Dashboard | 'What Matters Now' AI market summary card | Key: Claude | 1.5 | 0.5 | 2 | P0 | 61
W7 | 24 Aug | 28 Aug | Stock Detail | AI thesis + risk + confidence score | Key: Claude | 2 | 1 | 3 | P1 | 64
W7 | 24 Aug | 28 Aug | Stock Detail | AI technical analysis (4 tone modes) | Key: Claude | 1.5 | 0.5 | 2 | P1 | 66
W7 | 24 Aug | 28 Aug | Earnings Hub | AI earnings summary (what happened / beat-miss / guidance) | Key: Claude | 1.5 | 0.5 | 2 | P1 | 68
W7 | 24 Aug | 28 Aug | Analyst / Insider / Watchlist | AI note per action + 13F digest + watchlist AI | Key: Claude | 2 | 1 | 3 | P2 | 71
W8 | 31 Aug | 04 Sep | Analyst Actions | Procure Benzinga; build analyst-action-events job (per-firm upgrades/downgrades/PT) | Key: Benzinga | 3.5 | 1 | 4.5 | P0 | 75.5
W8 | 31 Aug | 04 Sep | Earnings Hub | Guidance status + price reaction + real-time actuals + tag pills | Key: Benzinga | 2.5 | 1 | 3.5 | P0 | 79
W8 | 31 Aug | 04 Sep | Watchlist / News | Upside% vs analyst PT + richer news category tags | Key: Benzinga | 1 | 0.5 | 1.5 | P1 | 80.5
W9 | 07 Sep | 11 Sep | Options Chain | Options flow + dark-pool prints | Key: Unusual Whales / Polygon-paid | 3 | 1 | 4 | P2 | 84.5
W9 | 07 Sep | 11 Sep | Portfolio / Watchlist | Alerts engine: 12 alert types + watchlist alert pills/toggle | — | 3 | 1.5 | 4.5 | P0 | 89
W9 | 07 Sep | 11 Sep | Stock Detail | Intraday (1D/1W) charts + 5Y history | Key: Polygon-paid | 2 | 1 | 3 | P1 | 92
W10 | 14 Sep | 18 Sep | Themes / Screener / Movers | Editorial + dropped-feature decisions (theme list, presets, trending/gaps/weekly/my-names) | — | 2 | 1 | 3 | P1 | 95
W10 | 14 Sep | 18 Sep | Earnings / Macro | Calendars on real date ranges (structural rework) | — | 2 | 1 | 3 | P0 | 98
W10 | 14 Sep | 18 Sep | All | Full regression + empty-states + mobile + performance + security review | — | 1 | 4 | 5 | P0 | 103
WEEK TOTALS
W1 | 13 Jul – 17 Jul |  | 16.0 person-days
W2 | 20 Jul – 24 Jul |  | 9.0 person-days
W3 | 27 Jul – 31 Jul |  | 10.0 person-days
W4 | 03 Aug – 07 Aug |  | 10.5 person-days
W5 | 10 Aug – 14 Aug |  | 8.0 person-days
W6 | 17 Aug – 21 Aug |  | 7.5 person-days
W7 | 24 Aug – 28 Aug |  | 10.0 person-days
W8 | 31 Aug – 04 Sep |  | 9.5 person-days
W9 | 07 Sep – 11 Sep |  | 11.5 person-days
W10 | 14 Sep – 18 Sep |  | 11 person-days
TOTAL |  |  | 103.0 person-days over 10 weeks (13 Jul – 18 Sep 2026)